## CRONOGRAMA
FEITO | DIA | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | X
AGENDADO | SESSÃO (6h - CADA QUADRADO EQUIVALE A 90 MINUTOS)
EM CURSO
ATRASO
URGENTE | 1. Planning and setup
PITSTOP : APRESENTAÇÃO DO PROJECTO
BACKEND PROJECT : SESSÃO 01
BACKEND PROJECT : SESSÃO 02
Sprint schedule locked
Write project brief (scope, MVP, future roadmap)
ER diagram + database schema
Draft project brief (scope, roadmap, vision)
Project structure setup (folders, configs, auth basics)
Initialize repo + environment configs
Set up Express/NestJS/Django skeleton
Configure DB connection
2. Development
BACKEND PROJECT : SESSÃO 03
Implement Product CRUD endpoints
Implement Retailer CRUD endpoints
Add validation middleware
Write unit tests for Product + Retailer
Create basic dashboard layout (navigation buttons)
Build Product list view (fetch from backend)
Simple form for adding products
3. Orders + Status + Frontend Integration
BACKEND PROJECT : SESSÃO 04
BACKEND PROJECT : SESSÃO 05
Order table logic (link product, retailer, team)
Status tracking (in stock, waiting delivery, sold, wasted)
Movement history logging (optional but impressive)
Product list view (pulls from backend)
Simple forms for CRUD (add/edit product, retailer, order)
4. Visually Ready Demo
BACKEND PROJECT : SESSÃO 06
BACKEND PROJECT : SESSÃO 07
BACKEND PROJECT : SESSÃO 08
Dashboard with Products, Retailers, Orders
Tables/lists showing data with status
Example flows to be shown/presented
Error handling middleware
Seed data for demo (sample products, retailers, orders)
5. Refinement
Authentication (JWT, role-based access)
Improve test coverage
Polish frontend interactions (reset, delete, update flows)
6. Final Polish & Delivery
Ensure migrations/seeds work cleanly
Clean code and comments
Documentation, reference to future improvements
Self-assessment
Deliver project with README + API docs
ENTREGA

## FICHEIROS
15_Projeto Pratico II/
| mario_silva/ | cliente/ | brandbook_interactivo
grafica / formadora/